## Sheet1
| البند | التوصيف |  |  |  |  | النسبة |  | معاينة | النسب المعتمدة | نسبة المعاينة | التقييم | Notes
1 | تجهيز الموقع (PRELIMINARIES) | Site trailer + temporary fence + signboard + soil testing |  |  |  |  | 2% | 45% | 100% | 45% | 0.9% | 2%
|  | Working (executive) drawings | [5 empty] | 15% | 100% | 15% | 0.3%
|  | Temporary electricity & water lines + site cleaning | Temporary electricity & water lines + site cleaning | Temporary electricity & water lines + site cleaning | Temporary electricity & water lines + site cleaning | Temporary electricity & water lines + site cleaning |  | 40% | 100% | 40% | 0.8%
2 | أعمال الأساسات (EXCAVATION AND SUBSTRUCTURE WORK) | Excavation | Excavation | Excavation | Excavation | Excavation | 13% | 3.75% | 100% | 3.75% | 0.4875% | 13%
|  | Piles for footing | Piles for footing | Piles for footing | Piles for footing | Piles for footing |  | 50% | 100% | 50% | 6.5%
|  | Pile cap (or tie beam) and neck columns | Pile cap (or tie beam) and neck columns | Pile cap (or tie beam) and neck columns | Pile cap (or tie beam) and neck columns | Pile cap (or tie beam) and neck columns
|  | Ground beams | Ground beams | Ground beams | Ground beams | Ground beams |  | 35% | 100% | 35% | 4.55%
|  | Backfilling | Backfilling | Backfilling | Backfilling | Backfilling |  | 3.75% | 100% | 3.75% | 0.4875%
|  | Ground-slab concrete | Ground-slab concrete | Ground-slab concrete | Ground-slab concrete | Ground-slab concrete |  | 7.5% | 100% | 7.5% | 0.975%
3 | الخرسانات (SUPER-STRUCTURE) | Ground-floor columns | Ground-floor columns | Ground-floor columns | Ground-floor columns | Ground-floor columns | 17% | 7.5% | 100% | 7.5% | 1.275% | 17%
|  | First-floor columns | First-floor columns | First-floor columns | First-floor columns | First-floor columns |  | 7.5% | 100% | 7.5% | 1.275%
|  | Ground-floor slab | Ground-floor slab | Ground-floor slab | Ground-floor slab | Ground-floor slab |  | 37.5% | 100% | 37.5% | 6.375%
|  | First-floor slab | First-floor slab | First-floor slab | First-floor slab | First-floor slab |  | 37.5% | 100% | 37.5% | 6.375%
|  | Roof + parapet + decorative finishes | Roof + parapet + decorative finishes | Roof + parapet + decorative finishes | Roof + parapet + decorative finishes | Roof + parapet + decorative finishes |  | 10% | 100% | 10% | 1.7%
4 | أعمال المباني (BLOCKSWORK) | Plastering | Plastering | Plastering | Plastering | Plastering | 5% | 10% | 100% | 10% | 0.5% | 5%
|  | Ground floor | Ground floor | Ground floor | Ground floor | Ground floor |  | 45% | 100% | 45% | 2.25%
|  | First floor | First floor | First floor | First floor | First floor |  | 45% | 100% | 45% | 2.25%
|  | Roof + parapet | Roof + parapet | Roof + parapet | Roof + parapet | Roof + parapet |  | 0% | 100% | 0% | 0%
5 | العزل (WATERPROOFING-WORK) | Foundations | Foundations | Foundations | Foundations | Foundations | 3% | 15% | 100% | 0.15 | 0.45% | 2.79%
|  | First-floor bathrooms | First-floor bathrooms | First-floor bathrooms | First-floor bathrooms | First-floor bathrooms |  | 15% | 100% | 15% | 0.45%
|  | Roof waterproofing + terrazzo | Roof waterproofing + terrazzo | Roof waterproofing + terrazzo | Roof waterproofing + terrazzo | Roof waterproofing + terrazzo |  | 70% | 90% | 63% | 1.89%
6 | التشطيبات (FINISHING-WORK) | Plastering | Interior | 22% | Exterior | 13% | 19% | 35% | 100% | 35% | 6.65% | 18.18%
|  | Painting | Interior | 13% | Exterior | 9% |  | 22% | 85% | 18.7% | 3.553%
|  | Ceramic | wall | 11% | Flooring | 22% |  | 33% | 100% | 33% | 6.27%
|  | Suspended ceilings | [5 empty] | 2% | 70% | 1.4% | 0.266%
|  | Stairs & entrance marble | [5 empty] | 8% | 95% | 7.6% | 1.444%
7 | أعمال النجارة (JOINERY AND IRONMONGERY WORK) | Zafra frames (sub-frame) |  |  |  |  | 5% | 5% | 100% | 5% | 0.25% | 4%
|  | Frames | [5 empty] | 25% | 100% | 25% | 1.25%
|  | Leaf-type doors | [5 empty] | 30% | 100% | 30% | 1.5%
|  | Painting & accessories | [5 empty] | 20% | 100% | 20% | 1%
|  | Wooden cabinets | [5 empty] | 20% | 0% | 0% | 0%
8 | أعمال الألمونيوم(ALUMINIUM AND GLASS WORK) | window | Frames | 20% | Sliding Windows | 25% | 7% | 45% | 100% | 45% | 3.15% | 6.493%
|  | Glass | [5 empty] | 15% | 85% | 12.75% | 0.8925%
|  | Kitchen cabinets | [5 empty] | 20% | 80% | 16% | 1.12%
|  | Stair handrail | [5 empty] | 20% | 95% | 19% | 1.33%
9 | أعمال الكهرباء (ELECTRIC WORK ) | Pipes & Junction Boxes |  | floor | first | roof | 7% | 20% | 100% | 20% | 1.4% | 5.338% | تمديدات المواسير الاسقف 1/3 تمديدات المواسير الجدران 1/3 تمديدات المواسير الارضيات 1/3
|  | Electrical Wiring Installations |  | floor | first | roof |  | 30% | 100% | 30% | 2.1%
|  | Distribution board (DB) | [5 empty] | 5% | 100% | 5% | 0.35%
|  | Breakers | [5 empty] | 5% | 95% | 4.75% | 0.3325%
|  | Cable | [5 empty] | 15% | 90% | 13.5% | 0.945%
|  | Socket & switch | [5 empty] | 5% | 0% | 0% | 0%
|  | Main DB & exhaust fans | [5 empty] | 10% | 30% | 3% | 0.21%
|  | Municipality handover & fees | [5 empty] | 10% | 0% | 0% | 0%
10 | أعمال التكييف (AC WORK ) | Water drainage pipes |  |  |  |  | 7% | 5% | 100% | 5% | 0.35% | 3.29% | في حالة الدكتات نحاس + دكتات + صرف 30 مكائن داخلية 30 مكائن خارجية 30 اختبار + تسليم 10
|  | Copper | [5 empty] | 20% | 95% | 19% | 1.33%
|  | Foundations | [5 empty] | 5% | 100% | 5% | 0.35%
|  | Indoor units | [5 empty] | 30% | 30% | 9% | 0.63%
|  | Outdoor units | [5 empty] | 30% | 30% | 9% | 0.63%
|  | Testing & commissioning | [5 empty] | 10% | 0% | 0% | 0%
11 | التركيبات الصحية (SANITARY WORK) | Water feed & risers |  |  |  |  | 6% | 15% | 100% | 15% | 0.9% | 4.47%
|  | Drainage & risers | [5 empty] | 25% | 100% | 25% | 1.5%
|  | Sanitary fixtures | [5 empty] | 25% | 50% | 12.5% | 0.75%
|  | Overhead tanks & connections | [5 empty] | 7.5% | 90% | 6.75% | 0.405%
|  | Ground tanks & connections | [5 empty] | 7.5% | 30% | 2.25% | 0.135%
|  | Water heaters | [5 empty] | 5% | 100% | 5% | 0.3%
|  | Manholes & external connections | [5 empty] | 10% | 80% | 8% | 0.48%
|  | Municipality handover & fees | [5 empty] | 5% | 0% | 0% | 0%
12 | الأعمال الخارجية (EXTERNAL WORK) | Concreting (boundary wall & guard room) |  |  |  |  | 9% | 35% | 100% | 35% | 3.15% | 6.66%
|  | Block Work | [5 empty] | 15% | 100% | 15% | 1.35%
|  | Plaster | [5 empty] | 15% | 100% | 15% | 1.35%
|  | Painting | [5 empty] | 10% | 90% | 9% | 0.81%
|  | Lighting | [5 empty] | 5% | 0% | 0% | 0%
|  | Garage gates & Interlock | [5 empty] | 20% | 0% | 0% | 0%
|  | TOTAL PERCENTAGE |  |  |  |  | 100% |  | 0% |  |  | 88.22%
المقاول | [6 empty] | 0 |  |  |  | المالك